## Slide 1: Remote Startup Welcome Kit
Project Goal: Create a warm, digital savvy 1-week onboarding experience
Stakeholders: HR Lead, IT Support, Manager, Buddy
New Hire Persona: Experienced professional transitioning into remote work

## Slide 2: CHALLENGES IN CURRENT ONBOARDING
No structured onboarding → new hires feel lost.
Overwhelm from too many tools, no clear guidance.
Lack of early connections → low engagement and productivity

## Slide 3: WELCOME KIT OVERVIEW
Persona-based design: Jordan Williams (Marketing Associate).
Journey Map (Day 0-5) staged rollout from preboarding → first task.
Toolkit
Playbook (values, communication, norms, tools)
Checklists (IT, HR, first week tasks)
FAQs (simple answers to common issues)
Sample Welcome Note (warm introductions)

## Slide 4: RACI AND RISK MANAGEMENT
RACI Matrix
HR = Accountable for onboarding
IT = Responsible for access
Manager = Assigns first task
Buddy = Provide support
Risk Management
Provision IT accounts on Day 0.
Daily drip of content to avoid overwhelm
Backup buddy assigned
Manager reviews first task clarity

## Slide 5: Measuring Success
Key Metrics
100% IT+HR setup complete by Day 2.
90% first task completion by Day 5
Satisfaction ≥ 4/5 on onboarding survey
Next Steps
Pilot Welcome Kit with first new hires.
Collect feedback & iterate.
Scales to future hires.